## Green
EE1000 2023 Baby Soother Group Project - Robotic Bird Toy
Group 3
V1 last modified by Alex
Project start date: | 2023-11-02 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 2 | 2 |  |  | November | [34 empty] | December
 | time axis 2023-11-02 to 2023-12-27
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-11-02 to 2023-12-27
Idea Development
First Risk Assesment | Joshua | 100% | 2023-11-02 | 9
Market Research | Sabira | 100% | 2023-11-10 | 7
Idea Brainstroming | Everyone | 100% | 2023-11-02 | 15
Check Component Pricing | Sabira | 100% | 2023-11-10 | 7
Initial idea proposal | Everyone | 100% | 2023-11-16 | 1 | 2023-11-16: 2
Initial Design
First draft of CAD design | Alex | 100% | 2023-11-10 | 9
Protoype electronics ideas | Alex | 50% | 2023-11-15 | 10
Develop initial code | Solomon | 33% | 2023-11-16 | 15
Send bill of materials | Sabira | 100% | 2023-11-17 | 1 | 2023-11-17: 2
Prototype Development
Finalize CAD design | Alex | 70% | 2023-11-16 | 9
Send CAD files to printer & laser | Alex | 0% | 2023-11-24 | 1 | 2023-11-24: 2
Assemble 3D print | Alex, Joshua | 0% | 2023-11-25 | 3
Solder internal electronics | Alex, Joshua, Solomon | 0% | 2023-11-25 | 3
Finalize code | Joshua, Jack | 20% | 2023-11-30 | 8
Full prototype | Everyone | 0% | 2023-12-07 | 1 | 2023-12-07: 2
Final Presentation
Make PowerPoint | Joshua, Sabira, Alex | 0% | 2023-11-30 | 8
Practice presentation | Everyone | 0% | 2023-12-06 | 3
Issues/bugs | Everyone | 2% | 2023-11-30 | 9
Dragons Den | Everyone | 0% | 2023-12-08 | 1 | 2023-12-08: 2
To add more data, Insert new rows ABOVE this one

## Changelog
Version | Contributor | Notes
V1 | Alex | Created initial Gantt chart.